## By month
DONE | MONTH SCHEDULED | BY | NOTES
JUNE
| Request BP write-up from DJS | YE
| Request Symposiuim write-up from MH | YE
JULY
| Determine BP pictures to use | MWG/TF
| Determine Symposium pictures to use | MWG/TF
| Bradley Prizes write-up completed; to YE | DJS
| Symposium write-up completed; to YE | MEH
| BP write-up done in AR-draft | YE
| Place BP pictures | YE
| Symp write-up done in AR-draft | YE
| Place Symposium pictures | YE
AUGUST
| Prepare AR and R-WI budgets | YE
| Contact Lithoprint to request quote | YE
| Contact EXG to request quote | YE
| Ask MWG if any major style changes to AR | YE
| Ask MWG if any major style changes to WI-R | YE
| Confirm GCCs, BPS, BF handled same as prior year | YE
SEPTEMBER
| Directors photo provided to YE | TF
| Lithoprint quote received | YE
| Request cover samples from printer | YE
| Receive cover samples | YE
OCTOBER
| Determine quantity of AR | TF/YE
| Determine quantity of WI Report | TF/YE
| Determine quantity of President enclosure cards | TF
| Determine cover stock & color | TF/YE
| Determine Inside stock & color | TF/YE
| Receive style changes for AR, if any | YE
| Receive style changes for R-WI, if any | YE
NOVEMBER
| Request program area & text description changes (format), if any | YE
| Request updated mailing lists (GMC, DF, MMAC) | TF
| Request media list from Mueller Com | TF
| Provide staff photo to YE | TF
| Staff photo received and placed into AR | YE
| Staff photo received and placed into WI-R | YE
| Ask MWG if he wants a cover letter sent with WI Rept (enc. Sample) | YE
| AR text and style changes (if any) to YE | YE
| AR text and style changes (if any) to YE | YE
| Grants list to program staff for editing of descriptions | YE
DECEMBER
| Update GMC, DF, MMAC mail lists in E-Tapestry | YE
| Text and style changes completed for AR | YE
| Text and style changes completed for R-WI | YE
| Export grants from Gifts | YE
| Format exported lists for AR | YE
| Format exported lists for R-WI | YE
| Enter grants into AR document | YE
| Provide AR draft to Program Staff | YE
| Provide AR draft to MWG/DPS/CF/TF/MH | YE
| Select foil and ink colors | TF/YE
| Changes on AR returned to YE | Staff
| Changes on AR returned to YE | VP
| Changes to AR completed | YE
| Run grant tape total; check all grants entered on AR | YE
| Receive media lists | TF
| Media list to YE | TF
| Format media list | YE
| Run Gifts mailing list | YE
| Run E-Tapestry mailing list | YE
| Combine Gifts and e-Tapestry mail lists | YE
| Prepare and circulate AR mail list | YE
| Return mail list changes to YE | PS
| Add media list to AR mail list | YE
| AR mail list changes completed | YE
JANUARY
| Enter grants into R-WI document | YE
| Send AR mail list to printer | YE
| President's letter for R-WI to YE | MWG
| Draft of President's letter completed | YE
| Final of President's letter completed | YE
| Provide R-WI draft to Program Staff | YE
| Provide R-WI draft to MWG/DPS/CF/TF/MH | VP
| Changes to R-WI returned to YE | Staff
| Changes to R-WI returned to YE | VP
| Changes to R-WI completed | YE
| Run grant tape total; check all grants entered on R-WI | YE
| Continue with changes and review by staff of AR | YE
| Continue with changes and review by staff of R-WI | YE
| Prepare and circulate R-WI mail list | YE
| Return R-WI mail list changes to YE | Staff
FEBRUARY
| R-WI mail list changes completed | YE
| R-WI mail list sent to printer | YE
| Financial Highlights to YE | MLH
| Draft of financial highlights to MLH for review | YE
| Reconcile grants listing with financial statement | YE
| Provide final AR w/reports, tape totals to CF | YE
| Final review of AR returned to YE | CF
| Final AR changes made | YE
| AR CD prepared for printer | YE
| AR CD sent to printer w/color copy | YE
| Provide final R-WI w/reports, tape totals to CF | YE
| Final review of R-WI returned to YE | CF
| Final R-WI changes made | YE
| R-WI CD prepared for printer | YE
| R-WI CD sent to printer w/color copy | YE
| President's letter sent to printer | YE
| AR proof received | YE
| AR proof reviewed | YE
| AR proof acceptance form signed and returned | YE
| R-WI proof received | YE
| R-WI proof reviewed | YE
| R-WI proof acceptance form signed and returned | YE
| 20 AR received | YE
| 20 R-WI received | YE
| AR mailed | LP
| R-WI mailed | LP
| Remainder AR delivered | LP
| Remainder R-WI delivered | LP
| Invoice received | YE