## MINE
TIMELINE FOR 2012 ANNUAL & WI REPORTS | BY | DONE | NOTES | NOTES for 2013 Reports
Primary Reviewers: CF& MEH
JUNE of 2012
Request BP write-up from DJS | YE | 2012-06-27
Request Symposium write-up from MH | YE | 2012-06-27
Basic template updates, i.e. change year | YE | 2012-06-27
JULY of 2012
Determine BP pictures to use & inform YE | TF | 2012-08-05
Determine Symposium pictures to use & inform YE | MEH | 2012-08-03
Bradley Prizes write-up completed; to YE | DJS | 2012-06-27
Symposium write-up completed; to YE | MEH | 2012-07-06
BP write-up done in AR-draft | YE | 2012-06-27
Place BP pictures | YE | 2012-09-06
Symp write-up done in AR-draft | YE | 2012-07-06
Place Symposium pictures | YE | 2012-08-03
AUGUST of 2012
Contact Lithoprint to request quote | YE | 2012-08-27
Contact EXG to request quote? | YE | n/a 2012
Ask MWG if any major style changes to AR | YE | 2012-11-29
Ask MWG if any major style changes to R-WI | YE | 2012-11-29
Confirm GCCs, BPS, BF handled same as prior year | YE | 2012-11-29
MWG response received re AR changes | YE | 2012-12-03
MWG response received re R-WI changes | YE | 2012-12-03
Convey MWG request for style changes, if any, to program staff | YE | n/a 2012
Take count of reports left from two years ago | YE | 2013-12-21
SEPTEMBER of 2012
Directors photo provided to YE | TF | 2012-06-13
Lithoprint quote received | YE | 2012-10-18
EGX quote received | YE | n/a '12
Directors photo placed in document | YE | 2013-01-03
Prepare AR & R- WI budgets; to TF | YE | 2012-09-06
Request cover samples from printer | YE | 2012-11-29
Receive cover samples | YE | 2012-12-27
OCTOBER of 2012
Ask Bill how many reports remain from last year | YE | 2012-12-27
Determine quantity of AR | TF/YE | 2013-01-02
Determine quantity of R-WI | TF/YE | 2013-01-02
Determine quantity of President enclosure cards | TF
Determine cover stock & color | TF/YE | 2012-12-27 | Curious metallics, #80-nude
Determine Inside stock & color | TF/YE | 2012-12-27
Receive style changes from Program staff for AR, if any | YE | n/a
Receive style changes from Program staff for R-WI, if any | YE | n/a
Inform printer of stock, color, quantity | YE | 2013-01-02
NOVEMBER of 2012
Ask TF to request updated mail lists (GMC, DF, MMAC) | YE | 2012-10-22
Request sector descrip text changes from program staff, if app. | YE | n/a
Provide staff photo to YE | TF | 2012-09-21
Staff photo received and placed into AR | YE | 2012-11-16
Staff photo received and placed into R-WI | YE | 2012-11-16
Ask MWG: cover letter w/WI Rept (encl. Sample) | YE | 2013-01-09
AR text and style changes completed | YE | n/a
R-WI text and style changes completed | YE | n/a
Grants list to CF & MH for editing of descriptions | YE | 2013-01-03
OR Use descriptions already on website from MH? | YE | n/a
Sector description text changes to YE (previous style) | PS | n/a
Sector description text changes completed (previous style) | YE | n/a
Return to program staff for proof & sign-off (w/marked copy)-prior | YE | n/a
DECEMBER of 2012
Provide web-site list of grants to YE | MEH | n/a
Updated mail lists to YE | TF | 2012-10-29
Update GMC, DF, MMAC mail lists in E-Tapestry | YE | 2012-11-06
Enter grants into AR document | YE | 2012-12-07 | started 12/3
Enter grants into R-WI document | YE | 2013-01-15
Run grant tape totals; check all grants entered on AR | YE | 2012-12-07
Run grant tape totals; check all grants entered on R-WI | YE | 2013-01-21
Provide AR draft to Primary Reviewers | YE | 2013-01-03
Provide R-WI draft to Primary Reviewers | YE | 2013-01-22
Changes to AR returned to YE | CF
Changes to AR returned to YE | MH
Changes to R-WI returned to YE | CF
Changes to R-WI returned to YE | MH
Changes made to AR | YE
AR back to Reviewers for sign-off (w/marked copy) | YE
Return approved AR to YE | CF
Return approved AR to YE | MH
Changes made to R-WI | CF
Changes made to R-WI | MH
R-WI back to Reviewers for sign-off (w/marked copy) | YE
Return approved R-WI to YE | CF
Return approved R-WI to YE | MH
Run grant tape total; check all grants entered on AR | YE
Run grant tape total; check all grants entered on R-WI | YE
Prepare reconciliation of grants to financial statement | YE
Provide AR draft to CF w/reconciliation to financial stmt | YE
AR draft returned to YE | CF
CF changes to AR completed | YE
Return to CF for approval and sign-off (w/marked copy) | YE
Return approved report to YE | CF
Provide AR draft to MWG | YE
AR draft returned to YE | MWG
MWG changes to AR completed | YE
Return AR to MWG for proof & sign-off (w/marked copy) | YE
Return AR to YE | MWG
Provide R-WI draft to CF w/tape totals attached | YE
R-WI draft returned to YE | CF
Changes to R-WI completed | YE
Return to CF for approval and sign-off (w/marked copy) | YE
Return R-WI to YE | CF
Provide R-WI draft to MWG | YE
R-WI draft returned to YE | MWG
MWG changes to R-WI completed | YE
Return to MWG for proof and sign-off (w/marked copy) | YE
Return to YE | MWG
JANUARY of 2013
Select foil and ink colors; inform printer | TF/YE | 2013-01-02
Return mail list changes to YE | PS
Mail list with recommended changes to MWG for approval | YE
Mail list changes returned to YE | MWG
AR mail list changes completed | YE
R-WI mail list prepared (pulled from AR mail list) | YE
R-WI mail list to MWG for review | YE
R-WI mail list returned to YE | MWG
R-WI mail list completed | YE
Send AR mail list to printer | YE
Send R-WI mail list to printer | YE
President's letter for R-WI to YE (if needed) | MWG | 2013-01-15
Update of President's letter completed | YE | 2013-01-18
Letter to MWG | YE
Letter returned to YE | MWG | 2013-01-18
Changes made to letter | YE | 2013-01-18
Return to MWG for proof and sign-off (w/marked copy) | YE | 2013-01-18
Final of President's letter completed | YE
Letters printed in-house for printer to enclose | YE
Provide final AR draft to MWG/CF/DPS/TF for sign off (ex: FiHi) | YE
Provide final R-WI draft to MWG/CF/DPS/TF for sign off | YE
AR draft returned to YE | VPs
R-WI draft returned to YE | VPs
Changes to AR completed and returned to reviewer (w/marked copy) | YE
Changes to R-WI completed and returned to reviewer (w/marked copy) | YE
Return AR to YE | Reviewer
Return R-WI to YE | Reviewer
Run & export mail list from e-Tapestry | YE
Format exported list for AR | YE
Run Gifts mailing list | YE
Format exported list for AR | YE
Combine Gifts and e-Tapestry mail lists | YE
Remove duplicates; review | YE
Route AR mail list to program staff | YE
FEBRUARY of 2013
AR mail list sent to printer | YE
R-WI mail list sent to printer | YE
Financial Highlights to YE (as soon after Feb. brd mtg as possible) | MLH
Financial highlights page prepared | YE
Draft of financial highlights to MLH for review | YE
Financial page returned to YE | MLH
Changes to financial highlights done | YE
Return to MLH for proof and sign-off (w/marked copy) | YE
Return Fi High to YE | MLH
Draft of financial highlights to CF for review and sign off | YE
Any changes to financial highlights to YE | CF
Changes to financial highlights completed | YE
Draft returned to CF for proof and sign-off (w/marked copy) | YE
Return Fi High to YE | CF
Draft of financial highlights to MWG for approval | YE
Financial highlights approved and returned to YE | MWG
MARCH OF 2013
AR packaged-software | YE
R-WI packaged-software | YE
AR CD prepared for printer | YE
R-WI CD prepared for printer | YE
Print color copy of AR for printer | YE
Print color copy of R-WI for printer | YE
CD of AR sent to printer w/color copy print-out | YE
CD of R-WI sent to printer w/color copy print-out | YE
President's letters sent to printer | YE
AR proof received | YE
AR proof reviewed | YE
Changes to printer | YE
Updated proof received | YE
AR proof reviewed | YE
AR proof to DPS for review and sign off | YE
AR proof to CF for review and sign off | YE
Return AR proof to YE | DPS
Return AR proof to YE | CF
AR to MWG for review and approval | YE
AR to YE with signed approval | MWG
R-WI proof received | YE
R-WI proof reviewed | YE
Changes to printer | YE
Updated proof received | YE
R-WI proof reviewed | YE
R-WI proof to DPS for review and sign off | YE
R-WI proof to CF for review and sign-off | YE
Return R-WI to YE | DPS
Return R-WI to YE | CF
R-WI to MWG for review and approval | YE
R-WI to YE with signed approval | MWG
Changes to AR returned to printer (if any) | YE
Changes to R-WI returned to printer (if any) | YE
New proofs received and reviewed | YE
AR proof acceptance form signed and returned | YE
R-WI proof acceptance form signed and returned | YE
20 AR received | LP
20 R-WI received | YE
AR mailed by printer | YE
R-WI mailed by printer | LP
Remainder AR delivered to Fdn. | YE
Remainder R-WI delivered to Fdn. | LP
2 Copies to each staff member | LP
Email to staff re: copy of the reports left on their desk | YE
Invoice received | YE
Invoice verified; sent to TF for sign-off | YE